## Sheet1
ID | Story | Estimation (hours) | Priority | Sprint When Finished | Domain | Status
1 | Design page mockups | 15 | 1 | 1 | Frontend
2 | Implement landing page | 5 | 3 | 1 | Frontend
3 | Implement class project webpage | 2 | 2 | 1 | Frontend
4 | Implement authentication frontend | 5 | 2 | 1 | Frontend
5 | Acquire a domain | 1 | 3 | 1 | Backend | Complete
7 | Implement CI/CD | 5 | 4 | 1 | Backend
10 | Design QR code generator | 3 | 4 | 1 | Backend
11 | Design overall project architecture | 10 | 1 | 1 | Both
11 | Design database | 10 | 1 | 1 | Backend
14 | Implement QR storage | 5 | 1 | 1 | Backend
| Authentication backend | 5
| QR code storage backend | 2
| QR code test coverage | 2
| Auth test coverage | 2
| Web form backend | 5
| Response backend | 5
6 | Implement user permissions | 10 | 3 | 2 | Backend
8 | Implement QR management portal | 8 | 1 | 2 | Both
9 | Implement QR form page | 8 | 1 | 2 | Both
12 | Implement API clients | 10 | 2 | 2 | Backend
13 | Design automated response service | 10 | 2 | 2 | Backend
12 | Implement metrics | 10 | 3 | 3 | Both